## Work Plan
Work plan
Task | Status | 2017 | [6 empty] | 2018 | [11 empty] | 2019
|  | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Literature survey
Literature survey | In progress | bar: 2017 June; 2017 Aug to 2019 Jan
Mungo Work
Generics | In progress | bar: 2017 June; 2017 Aug to 2017 Dec
Collections | Not started | bar: 2017 Oct to 2018 Aug
Exceptions | In progress | bar: 2018 Feb to 2018 Jul
Aliasing | Not started | bar: 2018 Apr to 2019 Jan
Context-free typestates | Not started | bar: 2017 June; 2017 Aug to 2018 Dec
StMungo Work
Keep up to date with Scribble and Mungo | In progress | bar: 2017 June; 2017 Aug to 2019 Feb
Support more Scribble constructs | Not started | bar: 2017 June; 2017 Aug to 2017 Dec
Integrate with Mungo | Not started | bar: 2018 Jan to 2018 Feb
Language usability and evaluation
Develop necessary methodology | In progress | bar: 2017 June; 2017 Aug to 2018 Oct
Develop necessary tools | In progress | bar: 2017 Aug to 2017 Dec
Evaluate Scribble | Not started | bar: 2018 Jan to 2018 May
Evaluate Mungo | Not started | bar: 2018 Sept to 2019 Feb
Evaluate through usecases | In progress | bar: 2017 Aug to 2018 Jan
Dissertation write-up
Literature survey Chapter | Not started | bar: 2018 Sept to 2018 Dec
Mungo Theoretical Work Chapter | Not started | bar: 2018 Nov to 2019 Apr
Mungo Practical Work Chapter | Not started | bar: 2018 Nov to 2019 Apr
StMungo Work Chapter | Not started | bar: 2018 Nov to 2019 Apr
Usability and evaluation Chapter | Not started | bar: 2018 Nov to 2019 Apr
Conclusion Chaper | Not started | bar: 2019 Mar to 2019 Apr
Additional chapters(optional) | Not started | bar: 2018 Nov to 2019 Apr

## Codes
Status
Not started
In progress
Complete
Overdue