## Work Plan
Work Plan Example www.tools4dev.org
Task | Responsible | Status | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Baseline survey
Design survey | Program Manager | Complete | bar: Year 1 1 to Year 1 2
Recruit data collectors | Program Manager | Complete | bar: Year 1 3
Collect data | Field Officers | Complete | bar: Year 1 4 to Year 1 5
Enter data | Admin Team | In progress | bar: Year 1 6
Analyse data | Technical Advisor | Overdue | bar: Year 1 6 to Year 1 7
Write report | Technical Advisor | Overdue | bar: Year 1 7
Stakeholder engagement
Stakeholder mapping | Program Manager | Complete | bar: Year 1 1
Orientation meetings | Program Manager | Complete | bar: Year 1 1 to Year 1 2
Quarterly meetings | Program Manager | In progress | bar: Year 1 3; Year 1 6; Year 1 9; Year 1 12; Year 2 3; Year 2 6; Year 2 9; Year 2 12; Year 3 3; Year 3 6; Year 3 9; Year 3 12
Newsletter updates | Program Manager | Not started | bar: Year 1 6; Year 1 12; Year 2 6; Year 2 12; Year 3 6; Year 3 12
Recruitment and training
Recruit peer educators | Training Manager | Not started | bar: Year 1 7 to Year 1 9
Training - HIV | Trainers | Not started | bar: Year 1 10 to Year 1 11
Training - Family planning | Trainers | Not started | bar: Year 1 11 to Year 1 12
Training - Nutrition | Trainers | Not started | bar: Year 1 12 to Year 2 1
Training - Gender based violence | Trainers | Not started | bar: Year 2 1 to Year 2 2
Training - WASH | Trainers | Not started | bar: Year 2 2 to Year 2 3
Campaign implementation
Run launch concert | Program Manager | Not started | bar: Year 2 4 to Year 2 6
Peer education sessions - District A | Peer Educators | Not started | bar: Year 2 7 to Year 2 12
Peer education sessions - District B | Peer Educators | Not started | bar: Year 2 9 to Year 3 2
Peer education sessions - District C | Peer Educators | Not started | bar: Year 2 11 to Year 3 4
Distribute posters and leaflets | Peer Educators | Not started | bar: Year 2 4 to Year 3 4
Endline survey and evaluation
Design survey and interviews | Program Manager | Not started | bar: Year 3 5 to Year 3 6
Recruit data collectors | Program Manager | Not started | bar: Year 3 7
Collect data | Field Officers | Not started | bar: Year 3 8 to Year 3 10
Enter data | Admin Team | Not started | bar: Year 3 11
Analyse data | Technical Advisor | Not started | bar: Year 3 11 to Year 3 12
Write report | Technical Advisor | Not started | bar: Year 3 12
This example by tools4dev is licensed under a Creative Commons Attribution-ShareAlike 3.0 Unported License.

## Codes
Status
Not started
In progress
Complete
Overdue